## WBS
Level | WBS | Task Description | Assigned To | Start | End | Notes
3 | 2024-01-03 | Définition des attendu des autres projets |  | 2023-11-13 | 2024-01-26 |  | 74 | 18.5
2 | 3.1.1 | Technology Discovery | Etienne / Hugo | 2023-11-13 | 2023-12-01
3 | 3.1.2 | Recrutement équipe L3 NFC Trace | Quentin / hugo | 2023-12-01 | 2023-12-19
4 | 3.1.3 | Requirements for M2 | Paul-Cesar / Etienne | 2023-12-19 | 2024-01-06
4 | 3.1.4 | Synthèse process | Etienne | 2024-01-06 | 1/26/24
4 | 3.2 | Modélisation des Intéractions avec la blockchain |  | 2024-01-29 | 2024-03-11 |  | 42 | 10.5
4 | 3.2.1 | Schéma relationnel : Traceability - blockchain | Hugo / Paul-Cesar | 2024-01-29 | 2024-02-08
3 | 3.2.2 | Schéma retionnel : Traceability - NFC Trace | Chadi | 2024-02-08 | 2024-02-18
4 | 3.2.3 | Schéma relationnel : NFT-NFC | Quentin | 2024-02-18 | 2024-02-28
4 | 3.2.4 | Create Schema for the smartContract | Chadi | 2024-02-28 | 2024-03-11
4 | 3.3 | Conception et développement des smart contracts |  | 2024-02-05 | 2024-04-29 |  | 84 | 21
3 | 3.2.1 | Checking roles | Etienne | 2024-02-05 | 2024-02-26
5 | 3.2.2 | manufacturedProduct From recipe | Etienne | 2024-02-26 | 2024-03-18
4 | 3.2.3 | Install Front | Chadi / Paul-Cesar | 2024-03-18 | 2024-04-08
6 | 3.3.4 | State machine solution | Etienne / Etienne | 2024-04-08 | 2024-04-29
3 | 3.4 | Modélisation du hardware |  | 2024-04-01 | 2024-05-13 |  | 42 | 10.5
2 | 3.4.1 | Setup Hardware | Hugo | 2024-04-01 | 2024-04-11
4 | 3.4.2 | Hardware prototyping | Hugo | 2024-04-11 | 2024-04-21
2 | 3.4.3 | List and check composants and Pi connection | Hugo | 2024-04-21 | 2024-05-07
5 | 3.4.4 | weld the pcb | Hugo | 2024-05-07 | 2024-05-13
4 | 2024-05-03 | Déploiement |  | 2024-04-15 | 2024-06-10 |  | 56 | 14
4 | 3.5.2 | Deploy on the cloud | Paul-Cesar / Etienne | 4/15/24 | 5/13/24
5 | 3.5.3 | Php Integration | Quentin | 5/13/24 | 5/27/24
3 | 3.5.4 | Stress Test on the blockchain | Etienne | 5/27/24 | 2024-06-10
3 | 2024-06-03 | Intégration des projets |  | 2024-05-13 | 2024-07-01 |  | 49 | 9.8
3 | 3.6.1 | Php Integration | Quentin | 2024-05-13 | 2024-05-22
3 | 3.6.2 | Writing Raymond's tasks | Quentin | 2024-05-22 | 2024-05-31
3 | 3.6.3 | API skeleton for raymond | Etienne | 2024-05-31 | 2024-06-09
3 | 3.6.4 | API test | Etienne | 2024-06-09 | 2024-06-17
4 | 3.6.5 | Stress Test on the blockchain | Paul-Cesar / Etienne | 2024-06-17 | 2024-07-01
Formulas:
End = [Start]+18
Start = [Start, row above]+18
Start = [End, row above]

## ©
Work Breakdown Structure
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.